## Inspections
RECORD | INSPECTOR | INSPECTION TYPE | INSPECTION DATE | RESULT | RESULT COMMENT
RES-2415274 | Paul Lovato | 29 Bldg FINAL | 2025-01-06 | Approved
RES-2415274 | Paul Lovato | 79 Elect FINAL | 2025-01-06 | Approved
RES-2415274 | Paul Lovato | 59 Plmg FINAL | 2025-01-06 | Approved
RES-2415274 | Paul Lovato | 39 Mech FINAL | 2025-01-06 | Approved
RES-2423855 | Paul Lovato | 29 Bldg FINAL | 2025-01-06 | Approved
RES-2423855 | Paul Lovato | 79 Elect FINAL | 2025-01-06 | Approved
RES-2423855 | Paul Lovato | 59 Plmg FINAL | 2025-01-06 | Approved
RES-2423855 | Paul Lovato | 39 Mech FINAL | 2025-01-06 | Approved
RES-2417521 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-01-07 | Approved
RES-2427420 | Paul Lovato | 41 Plmg-Top/Rough | 2025-01-07 | Approved
RES-2406487 | Paul Lovato | 29 Bldg FINAL | 2025-01-10 | Not Ready
RES-2406487 | Paul Lovato | 79 Elect FINAL | 2025-01-10 | Not Ready
RES-2406487 | Paul Lovato | 59 Plmg FINAL | 2025-01-10 | Not Ready
RES-2406487 | Paul Lovato | 39 Mech FINAL | 2025-01-10 | Not Ready
RES-2427678 | Paul Lovato | 47 Plmg-Gas Test-PGE | 2025-01-14 | Approved
RES-2500249 | Paul Lovato | 47 Plmg-Gas Test-PGE | 2025-01-15 | Approved
COM-2326169 | Paul Lovato | 19 Bldg-Frame | 2025-01-15 | Cancel | All rough inspections to be approved prior to frame inspection.
RES-2406487 | Paul Lovato | 39 Mech FINAL | 2025-01-17 | Approved
RES-2406487 | Paul Lovato | 59 Plmg FINAL | 2025-01-17 | Approved
RES-2406487 | Paul Lovato | 79 Elect FINAL | 2025-01-17 | Approved
RES-2406487 | Paul Lovato | 29 Bldg FINAL | 2025-01-17 | Approved
RES-2421923 | Paul Lovato | 81 Frame Across/Board | 2025-01-22 | Approved
COM-2426504 | Paul Lovato | 29 Bldg FINAL | 2025-01-23 | Approved
COM-2426504 | Paul Lovato | 39 Mech FINAL | 2025-01-23 | Approved
COM-2426504 | Paul Lovato | 59 Plmg FINAL | 2025-01-23 | Approved
COM-2426504 | Paul Lovato | 79 Elect FINAL | 2025-01-23 | Approved
RES-2421923 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-01-23 | Approved
COM-2425931 | Paul Lovato | 29 Bldg FINAL | 2025-01-29 | Approved
COM-2326169 | Paul Lovato | 19 Bldg-Frame | 2025-01-29 | Approved
RES-2500249 | Paul Lovato | 29 Bldg FINAL | 2025-01-31 | Correction Notice | 1) Provide address at front of dwelling. 2) Missing HVAC grills 3) Complete installation of appliances in kitchen. 4) Provide HERS test for new HVAC
RES-2500249 | Paul Lovato | 79 Elect FINAL | 2025-01-31 | Correction Notice | See Correction Notice at #29 Bldg Final
RES-2500249 | Paul Lovato | 59 Plmg FINAL | 2025-01-31 | Correction Notice | See Correction Notice at #29 Bldg Final
RES-2500249 | Paul Lovato | 39 Mech FINAL | 2025-01-31 | Correction Notice | See Correction Notice at #29 Bldg Final
COM-2326169 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-01-31 | Correction Notice | Missing screws throughout the new walls. Drywall not stopped on studs, so no edge screws.
RES-2419759 | Paul Lovato | 81 Frame Across/Board | 2025-02-03 | Correction Notice | Fire stop required on ceilings and walls adjacent to other units.
RES-2419759 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-02-03 | Approved
COM-2326169 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-02-04 | Re-Inspection Fee | 1) Pay re-inspection fee prior to any further inspections. 2) Licensed contractor required to be onsite prior to any other inspections called in.
RES-2502359 | Paul Lovato | 29 Bldg FINAL | 2025-02-05 | Approved
RES-2419759 | Paul Lovato | 81 Frame Across/Board | 2025-02-06 | Approved
RES-2500249 | Paul Lovato | 39 Mech FINAL | 2025-02-07 | Approved
RES-2500249 | Paul Lovato | 59 Plmg FINAL | 2025-02-07 | Approved
RES-2500249 | Paul Lovato | 79 Elect FINAL | 2025-02-07 | Approved
RES-2500249 | Paul Lovato | 29 Bldg FINAL | 2025-02-07 | Approved
RES-2419759 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-02-07 | Approved
RES-2417061 | Paul Lovato | 81 Frame Across/Board | 2025-02-10 | Approved
RES-2417521 | Paul Lovato | 81 Frame Across/Board | 2025-02-11 | Approved
RES-2501721 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-02-11 | Approved
RES-2425725 | Paul Lovato | 29 Bldg FINAL | 2025-02-12 | Approved
RES-2425725 | Paul Lovato | 79 Elect FINAL | 2025-02-12 | Approved
RES-2425725 | Paul Lovato | 59 Plmg FINAL | 2025-02-12 | Approved
RES-2425725 | Paul Lovato | 39 Mech FINAL | 2025-02-12 | Approved
COM-2418175 | Paul Lovato | 29 Bldg FINAL | 2025-02-14 | Approved
COM-2418175 | Paul Lovato | 79 Elect FINAL | 2025-02-14 | Approved
COM-2418175 | Paul Lovato | 39 Mech FINAL | 2025-02-14 | Approved
COM-2418175 | Paul Lovato | 59 Plmg FINAL | 2025-02-14 | Cancel | Duplicate request
COM-2418175 | Paul Lovato | 59 Plmg FINAL | 2025-02-14 | Approved
RES-2502953 | Paul Lovato | 29 Bldg FINAL | 2025-02-14 | Approved
RES-2502953 | Paul Lovato | 79 Elect FINAL | 2025-02-14 | Approved
COM-2427173 | Paul Lovato | 47 Plmg-Gas Test-PGE | 2025-02-14 | Approved
COM-2414626 | Paul Lovato | 29 Bldg FINAL | 2025-02-14 | Cancel | Approved finals from all other disciplines required prior to #29 Bldg final
COM-2326169 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-02-14 | Approved
RES-2417521 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-02-20 | Approved
RES-2417521 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-02-20 | Cancel | Duplicate entry
RES-2421923 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-02-20 | Approved
COM-2419023 | Paul Lovato | 29 Bldg FINAL | 2025-02-25 | Approved
COM-2424957 | Paul Lovato | 29 Bldg FINAL | 2025-02-25 | Approved
COM-2424957 | Paul Lovato | 59 Plmg FINAL | 2025-02-25 | Approved
COM-2503530 | Paul Lovato | 39 Mech FINAL | 2025-02-25 | Cancel | Inspection sent to correct inspector.
RES-2503505 | Paul Lovato | 39 Mech FINAL | 2025-02-25 | Cancel | Canceled per the owner
RES-2503505 | Paul Lovato | 79 Elect FINAL | 2025-02-25 | Cancel | Canceled per the owner
RES-2426520 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-02-25 | Cancel | Inspection cancelled and rescheduled to BI Lowther due to he is covering for case manager.
RES-2501721 | Paul Lovato | 81 Frame Across/Board | 2025-02-27 | Approved | Check hangers on copper piping in basement at insulation inspection.
RES-2501721 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-02-28 | Approved
COM-2419259 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-03-04 | Approved
RES-2427678 | Paul Lovato | 29 Bldg FINAL | 2025-03-04 | Approved
RES-2427678 | Paul Lovato | 79 Elect FINAL | 2025-03-04 | Approved
RES-2427678 | Paul Lovato | 59 Plmg FINAL | 2025-03-04 | Approved
RES-2502176 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-03-06 | Approved
RES-2419437 | Paul Lovato | 39 Mech FINAL | 2025-03-06 | Cancel | Fire final required prior to Bldg final
RES-2419437 | Paul Lovato | 59 Plmg FINAL | 2025-03-06 | Cancel | Fire final required prior to Bldg final
RES-2419437 | Paul Lovato | 79 Elect FINAL | 2025-03-06 | Cancel | Fire final required prior to Bldg final
RES-2419437 | Paul Lovato | 29 Bldg FINAL | 2025-03-06 | Cancel | Fire final required prior to Bldg final
COM-2419259 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-03-06 | Approved
RES-2502176 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-03-06 | Approved
COM-2419259 | Paul Lovato | 29 Bldg FINAL | 2025-03-07 | Approved
RES-2421272 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-03-07 | Approved
RES-2504146 | Paul Lovato | 29 Bldg FINAL | 2025-03-10 | Approved
RES-2504146 | Paul Lovato | 79 Elect FINAL | 2025-03-10 | Approved
RES-2504146 | Paul Lovato | 39 Mech FINAL | 2025-03-10 | Approved
RES-2504146 | Paul Lovato | 59 Plmg FINAL | 2025-03-10 | Approved
RES-2501959 | Paul Lovato | 79 Elect FINAL | 2025-03-11 | Cancel | Wrong inspection called in for.
RES-2501959 | Paul Lovato | 29 Bldg FINAL | 2025-03-11 | Cancel | Wrong inspection called in for.
RES-2501959 | Paul Lovato | 59 Plmg FINAL | 2025-03-11 | Cancel | Wrong inspection called in for.
RES-2501959 | Paul Lovato | 39 Mech FINAL | 2025-03-11 | Cancel | Wrong inspection called in for.
RES-2427420 | Paul Lovato | 59 Plmg FINAL | 2025-03-13 | Approved
RES-2420087 | Paul Lovato | 29 Bldg FINAL | 2025-03-14 | Approved
RES-2419759 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-03-18 | Approved
RES-2501721 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-03-20 | Approved
COM-2505226 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-03-25 | Approved
RES-2504857 | Paul Lovato | 29 Bldg FINAL | 2025-03-26 | Approved
RES-2504857 | Paul Lovato | 79 Elect FINAL | 2025-03-26 | Approved
RES-2504857 | Paul Lovato | 59 Plmg FINAL | 2025-03-26 | Approved
RES-2504857 | Paul Lovato | 39 Mech FINAL | 2025-03-26 | Approved
COM-2505869 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-03-27 | Approved
COM-2505869 | Paul Lovato | 19 Bldg-Frame | 2025-03-27 | Approved
RES-2417521 | Paul Lovato | 29 Bldg FINAL | 2025-03-28 | Approved
RES-2417521 | Paul Lovato | 79 Elect FINAL | 2025-03-28 | Approved
RES-2417521 | Paul Lovato | 59 Plmg FINAL | 2025-03-28 | Approved
RES-2417521 | Paul Lovato | 39 Mech FINAL | 2025-03-28 | Approved
COM-2505869 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-04-01 | Approved
RES-2502176 | Paul Lovato | 29 Bldg FINAL | 2025-04-02 | Approved
RES-2502176 | Paul Lovato | 79 Elect FINAL | 2025-04-02 | Approved
RES-2502176 | Paul Lovato | 59 Plmg FINAL | 2025-04-02 | Approved
RES-2502176 | Paul Lovato | 39 Mech FINAL | 2025-04-02 | Approved
COM-2413765 | Paul Lovato | 29 Bldg FINAL | 2025-04-04 | Approved
COM-2505226 | Paul Lovato | 29 Bldg FINAL | 2025-04-04 | Approved
RES-2419759 | Paul Lovato | 39 Mech FINAL | 2025-04-10 | Approved
RES-2419759 | Paul Lovato | 59 Plmg FINAL | 2025-04-10 | Approved
RES-2419759 | Paul Lovato | 79 Elect FINAL | 2025-04-10 | Approved
RES-2419759 | Paul Lovato | 29 Bldg FINAL | 2025-04-10 | Approved
COM-2427212 | Paul Lovato | 29 Bldg FINAL | 2025-04-14 | Approved
COM-2427212 | Paul Lovato | 39 Mech FINAL | 2025-04-14 | Approved
COM-2427212 | Paul Lovato | 59 Plmg FINAL | 2025-04-14 | Approved
COM-2427212 | Paul Lovato | 79 Elect FINAL | 2025-04-14 | Approved
COM-2326169 | Paul Lovato | 29 Bldg FINAL | 2025-04-21 | Cancel | Owner called and cancelled appointment
COM-2505869 | Paul Lovato | 29 Bldg FINAL | 2025-04-22 | Approved
COM-2505869 | Paul Lovato | 59 Plmg FINAL | 2025-04-22 | Approved
COM-2505869 | Paul Lovato | 79 Elect FINAL | 2025-04-22 | Approved
RES-2421923 | Paul Lovato | 29 Bldg FINAL | 2025-04-30 | Approved
RES-2421923 | Paul Lovato | 79 Elect FINAL | 2025-04-30 | Approved
RES-2421923 | Paul Lovato | 59 Plmg FINAL | 2025-04-30 | Approved
RES-2421923 | Paul Lovato | 39 Mech FINAL | 2025-04-30 | Approved
RES-2427976 | Paul Lovato | 19 Bldg-Frame | 2025-04-30 | Approved
RES-2418547 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-05-06 | Approved
RES-2418547 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-05-06 | Not Ready
RES-2418547 | Paul Lovato | 19 Bldg-Frame | 2025-05-06 | Cancel | Wrong inspection called in.
RES-2418547 | Paul Lovato | 41 Plmg-Top/Rough | 2025-05-06 | Cancel | Wrong inspection called in.
RES-2418547 | Paul Lovato | 31 Mech-Top/Rough | 2025-05-06 | Cancel | Wrong inspection called in
RES-2418547 | Paul Lovato | 81 Frame Across/Board | 2025-05-06 | Not Ready
COM-2326169 | Paul Lovato | 29 Bldg FINAL | 2025-05-15 | Approved
COM-2427173 | Paul Lovato | 29 Bldg FINAL | 2025-05-21 | Approved
COM-2427173 | Paul Lovato | 39 Mech FINAL | 2025-05-21 | Approved
COM-2427173 | Paul Lovato | 59 Plmg FINAL | 2025-05-21 | Approved
COM-2427173 | Paul Lovato | 79 Elect FINAL | 2025-05-21 | Approved
COM-2509332 | Paul Lovato | 29 Bldg FINAL | 2025-05-22 | Approved
COM-2509332 | Paul Lovato | 39 Mech FINAL | 2025-05-22 | Approved
COM-2500075 | Paul Lovato | 29 Bldg FINAL | 2025-05-27 | Approved
COM-2510325 | Paul Lovato | 29 Bldg FINAL | 2025-05-27 | Approved
RES-2501029 | Paul Lovato | 29 Bldg FINAL | 2025-06-04 | Not Ready | Prior to my arrival, Mech, Plmg, & electrical had corrections. I received a call from inspectors who stated I do not need to come by due to they are not ready for final inspection.
COM-2501851 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-06-05 | Cancel | I called requesting party to let him know I would be arriving onsite in 30 min. The requester stated he would like to cancel the inspection request and would be calling in for the following day.
COM-2501851 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-06-06 | Approved
COM-2501851 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-06-06 | Cancel
COM-2501851 | Paul Lovato | 19 Bldg-Frame | 2025-06-06 | Cancel | Wrong inspection called in for.
COM-2501851 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-06-06 | Approved
RES-2510845 | Paul Lovato | 81 Frame Across/Board | 2025-06-11 | Approved
RES-2510845 | Paul Lovato | 63 Elect-Rough | 2025-06-12 | Cancel | Wrong inspection called in for
RES-2510845 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-06-12 | Approved
RES-2501721 | Paul Lovato | 39 Mech FINAL | 2025-06-18 | Approved
RES-2501721 | Paul Lovato | 59 Plmg FINAL | 2025-06-18 | Approved
RES-2501721 | Paul Lovato | 79 Elect FINAL | 2025-06-18 | Approved
RES-2501721 | Paul Lovato | 29 Bldg FINAL | 2025-06-18 | Approved
RES-2427976 | Paul Lovato | 29 Bldg FINAL | 2025-06-18 | Approved
RES-2501959 | Paul Lovato | 29 Bldg FINAL | 2025-06-19 | Approved
RES-2501959 | Paul Lovato | 79 Elect FINAL | 2025-06-19 | Approved
RES-2501959 | Paul Lovato | 59 Plmg FINAL | 2025-06-19 | Approved
RES-2501959 | Paul Lovato | 39 Mech FINAL | 2025-06-19 | Approved
COM-2501851 | Paul Lovato | 29 Bldg FINAL | 2025-06-23 | Correction Notice | See correction notice at #39 Mech Final
COM-2501851 | Paul Lovato | 39 Mech FINAL | 2025-06-23 | Correction Notice | No heat or air to both units
COM-2501851 | Paul Lovato | 59 Plmg FINAL | 2025-06-23 | Approved
COM-2501851 | Paul Lovato | 79 Elect FINAL | 2025-06-23 | Approved
RES-2513133 | Paul Lovato | 29 Bldg FINAL | 2025-06-25 | Approved
RES-2513133 | Paul Lovato | 59 Plmg FINAL | 2025-06-25 | Approved
RES-2513133 | Paul Lovato | 79 Elect FINAL | 2025-06-25 | Approved
RES-2501959 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-06-25 | Approved
RES-2503582 | Paul Lovato | 29 Bldg FINAL | 2025-06-25 | Cancel
COM-2418789 | Paul Lovato | 12 Bldg-Concrete Slab Forms | 2025-06-25 | Not Ready
COM-2501851 | Paul Lovato | 29 Bldg FINAL | 2025-06-26 | Correction Notice | See correction notice on Mechanical final inspection
COM-2501851 | Paul Lovato | 39 Mech FINAL | 2025-06-26 | Correction Notice | Heat and air not working
RES-2511139 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-06-30 | Approved
RES-2511139 | Paul Lovato | 81 Frame Across/Board | 2025-06-30 | Approved
COM-2501851 | Paul Lovato | 29 Bldg FINAL | 2025-07-01 | Correction Notice | Heater not working in units
RES-2509323 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-07-01 | Approved | OK to pour footings.
RES-2511139 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-07-01 | Approved
RES-2509323 | Paul Lovato | 40 Plmg-Underfloor/Slab | 2025-07-01 | Approved
COM-2418789 | Paul Lovato | 12 Bldg-Concrete Slab Forms | 2025-07-02 | Approved
COM-2418789 | Paul Lovato | 40 Plmg-Underfloor/Slab | 2025-07-02 | Approved
RES-2503437 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-07-03 | Approved
RES-2509323 | Paul Lovato | 12 Bldg-Concrete Slab Forms | 2025-07-03 | Approved
RES-2511139 | Paul Lovato | 47 Plmg-Gas Test-PGE | 2025-07-07 | Approved
RES-2513777 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-07-07 | Approved
RES-2513693 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-07-08 | Approved
RES-2513777 | Paul Lovato | 29 Bldg FINAL | 2025-07-08 | Approved
COM-2501851 | Paul Lovato | 29 Bldg FINAL | 2025-07-09 | Approved
RES-2513693 | Paul Lovato | 29 Bldg FINAL | 2025-07-10 | Approved
RES-2509323 | Paul Lovato | 26 Bldg-Shear Nail | 2025-07-16 | Approved
RES-2509323 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-07-16 | Approved
RES-2508057 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-07-18 | Approved
RES-2503505 | Paul Lovato | 79 Elect FINAL | 2025-07-18 | Approved
RES-2503505 | Paul Lovato | 39 Mech FINAL | 2025-07-18 | Approved
RES-2502343 | Paul Lovato | 79 Elect FINAL | 2025-07-18 | Approved
RES-2502343 | Paul Lovato | 29 Bldg FINAL | 2025-07-18 | Approved
RES-2509323 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-07-21 | Approved
RES-2508353 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-07-22 | Approved
RES-2508353 | Paul Lovato | 11 Bldg-Ufer (Residential) | 2025-07-22 | Approved
RES-2406876 | Paul Lovato | 29 Bldg FINAL | 2025-07-23 | Approved
RES-2406876 | Paul Lovato | 79 Elect FINAL | 2025-07-23 | Approved
RES-2406876 | Paul Lovato | 59 Plmg FINAL | 2025-07-23 | Approved
RES-2406876 | Paul Lovato | 39 Mech FINAL | 2025-07-23 | Approved
RES-2508057 | Paul Lovato | 29 Bldg FINAL | 2025-07-31 | Approved
RES-2509323 | Paul Lovato | 63 Elect-Rough | 2025-08-01 | Cancel | Wrong inspection called in for
RES-2509323 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-08-01 | Approved
RES-2511139 | Paul Lovato | 29 Bldg FINAL | 2025-08-01 | Approved
RES-2511139 | Paul Lovato | 79 Elect FINAL | 2025-08-01 | Approved
RES-2511139 | Paul Lovato | 59 Plmg FINAL | 2025-08-01 | Approved
RES-2511139 | Paul Lovato | 39 Mech FINAL | 2025-08-01 | Approved
RES-2424922 | Paul Lovato | 81 Frame Across/Board | 2025-08-08 | Approved
RES-2508353 | Paul Lovato | 13 Bldg-Floor Joists/Girders | 2025-08-11 | Approved
RES-2508353 | Paul Lovato | 15 Bldg-Insulation Floor | 2025-08-11 | Approved
RES-2509323 | Paul Lovato | 81 Frame Across/Board | 2025-08-12 | Correction Notice | Plumbing not set o test. Bathtub / pan is to be installed. Ok to insulate.
COM-2418789 | Paul Lovato | 19 Bldg-Frame | 2025-08-15 | Correction Notice | All Rough disciplines to be approved prior to frame inspection.
COM-2418789 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-08-15 | Not Ready | OK to start building crickets for water drainage.
RES-2509323 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-08-15 | Approved
RES-2509323 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-08-15 | Correction Notice | Frame across the board approval required prior to insulation approval
RES-2513021 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-08-20 | Approved
RES-2513021 | Paul Lovato | 11 Bldg-Ufer (Residential) | 2025-08-20 | Approved
RES-2513021 | Paul Lovato | 40 Plmg-Underfloor/Slab | 2025-08-20 | Approved
RES-2508353 | Paul Lovato | 26 Bldg-Shear Nail | 2025-08-21 | Approved
RES-2508353 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-08-22 | Cancel
RES-2513021 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-08-22 | Approved
COM-2418789 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-08-25 | Approved
RES-2509323 | Paul Lovato | 81 Frame Across/Board | 2025-08-25 | Approved
RES-2509323 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-08-25 | Approved
RES-2517980 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-08-27 | Approved
COM-2418789 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-08-28 | Cancel
COM-2418789 | Paul Lovato | 20 Bldg-Frame (Walls Only) | 2025-08-28 | Cancel
COM-2418789 | Paul Lovato | 26 Bldg-Shear Nail | 2025-08-28 | Partial | Everything is good except the front entrance at the overhang.
RES-2517980 | Paul Lovato | 79 Elect FINAL | 2025-08-29 | Approved
RES-2517980 | Paul Lovato | 59 Plmg FINAL | 2025-08-29 | Approved
RES-2517980 | Paul Lovato | 29 Bldg FINAL | 2025-08-29 | Approved
COM-2418789 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-09-02 | Correction Notice | Curbs for mechanical system to be installed prior to roof installation.
COM-2418789 | Paul Lovato | 26 Bldg-Shear Nail | 2025-09-05 | Approved
COM-2517396 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-09-08 | Approved
COM-2418789 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-09-09 | Approved
COM-2418789 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-09-09 | Approved
COM-2418789 | Paul Lovato | 19 Bldg-Frame | 2025-09-09 | Partial | Ok to cover the exterior walls in order to start T-bar ceilings.
RES-2518788 | Paul Lovato | 13 Bldg-Floor Joists/Girders | 2025-09-10 | Approved | Prior to covering the walls. Electrical outlet buried in wall to be removed.
RES-2518905 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-09-11 | Approved
RES-2513021 | Paul Lovato | 81 Frame Across/Board | 2025-09-12 | Correction Notice | Shower pan to be installed to test connection to drain line.
RES-2513021 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-09-15 | Approved
RES-2504423 | Paul Lovato | 81 Frame Across/Board | 2025-09-16 | Approved
RES-2518788 | Paul Lovato | 29 Bldg FINAL | 2025-09-18 | Approved
RES-2518788 | Paul Lovato | 79 Elect FINAL | 2025-09-18 | Approved
RES-2518788 | Paul Lovato | 59 Plmg FINAL | 2025-09-18 | Approved
RES-2518905 | Paul Lovato | 29 Bldg FINAL | 2025-09-19 | Approved
COM-2418789 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-09-22 | Correction Notice | Rough HVAC inspection to be approved prior to this inspection.
COM-2418789 | Paul Lovato | 19 Bldg-Frame | 2025-09-25 | Approved
RES-2508353 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-09-26 | Correction Notice | Seal all penetrations, Install junction boxes for lighting and outlets. Fasten lath at areas where new meets existing. Install electrical service panel.
RES-2508353 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-09-26 | Approved
RES-2518868 | Paul Lovato | 41 Plmg-Top/Rough | 2025-09-26 | Cancel | Wrong inspection called in
RES-2518868 | Paul Lovato | 81 Frame Across/Board | 2025-09-26 | Approved
COM-2418789 | Paul Lovato | 22 Bldg-Sheetrock Nailing | 2025-09-29 | Approved
RES-2513021 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-10-10 | Approved
RES-2513021 | Paul Lovato | 81 Frame Across/Board | 2025-10-10 | Approved
RES-2513021 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-10-13 | Approved
RES-2504423 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-10-14 | Approved
COM-2418789 | Paul Lovato | 21 Bldg-Frame Ceiling (T-Bar) | 2025-10-15 | Approved
RES-2520987 | Paul Lovato | 29 Bldg FINAL | 2025-10-22 | Correction Notice | 1) Repair drywall around electrical panel. 2) Cover plates required on all electrical outlets and switches. 3) Add valves at water heater and repair drywall around water heater.
RES-2520987 | Paul Lovato | 79 Elect FINAL | 2025-10-22 | Correction Notice | See corrections under #29 Bldg Final
RES-2520987 | Paul Lovato | 59 Plmg FINAL | 2025-10-22 | Correction Notice | See corrections under #29 Bldg Final
RES-2510832 | Paul Lovato | 81 Frame Across/Board | 2025-10-23 | Approved
COM-2418789 | Paul Lovato | 29 Bldg FINAL | 2025-10-27 | Cancel
COM-2517396 | Paul Lovato | 29 Bldg FINAL | 2025-10-28 | Approved
RES-2519134 | Paul Lovato | 19 Bldg-Frame | 2025-11-07 | Info | Property owner called in inspection to show progress.
RES-2519228 | Paul Lovato | 79 Elect FINAL | 2025-11-12 | Approved
RES-2519228 | Paul Lovato | 39 Mech FINAL | 2025-11-12 | Approved
RES-2519228 | Paul Lovato | 29 Bldg FINAL | 2025-11-13 | Approved
RES-2516459 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-11-13 | Approved
COM-2418789 | Paul Lovato | 29 Bldg FINAL | 2025-11-13 | Approved
COM-2510515 | Paul Lovato | 29 Bldg FINAL | 2025-11-26 | Approved
COM-2510515 | Paul Lovato | 59 Plmg FINAL | 2025-11-26 | Approved
COM-2510515 | Paul Lovato | 79 Elect FINAL | 2025-11-26 | Approved
COM-2423194 | Paul Lovato | 29 Bldg FINAL | 2025-12-02 | Approved
COM-2423194 | Paul Lovato | 39 Mech FINAL | 2025-12-02 | Approved
COM-2423194 | Paul Lovato | 59 Plmg FINAL | 2025-12-02 | Approved
COM-2423194 | Paul Lovato | 79 Elect FINAL | 2025-12-02 | Approved
COM-2517281 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-12-02 | Approved
RES-2523950 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-12-02 | Cancel
RES-2523950 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-12-03 | Approved
COM-2517636 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-12-03 | Approved
RES-2524740 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-12-04 | Approved
COM-2426746 | Paul Lovato | 29 Bldg FINAL | 2025-12-05 | Approved
COM-2517636 | Paul Lovato | 18 Bldg-Exterior Lath/Siding | 2025-12-08 | Approved
RES-2509323 | Paul Lovato | 29 Bldg FINAL | 2025-12-08 | Approved
RES-2509323 | Paul Lovato | 79 Elect FINAL | 2025-12-08 | Approved
RES-2509323 | Paul Lovato | 59 Plmg FINAL | 2025-12-08 | Approved
RES-2509323 | Paul Lovato | 39 Mech FINAL | 2025-12-08 | Approved
RES-2520033 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-12-08 | Approved
RES-2520033 | Paul Lovato | 41 Plmg-Top/Rough | 2025-12-08 | Cancel
RES-2520033 | Paul Lovato | 81 Frame Across/Board | 2025-12-08 | Approved
COM-2518066 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-12-09 | Approved
RES-2506543 | Paul Lovato | 10 Bldg-Foundation Forms | 2025-12-09 | Approved
RES-2506543 | Paul Lovato | 14 Bldg-Insulation Wall | 2025-12-15 | Approved
RES-2506543 | Paul Lovato | 17 Bldg-Roof Plywood Nailing | 2025-12-15 | Approved
RES-2524677 | Paul Lovato | 67 Elect-Temp Power-SMUD | 2025-12-15 | Approved
RES-2506543 | Paul Lovato | 26 Bldg-Shear Nail | 2025-12-16 | Not Ready
RES-2506543 | Paul Lovato | 26 Bldg-Shear Nail | 2025-12-18 | Approved
RES-2524083 | Paul Lovato | 29 Bldg FINAL | 2025-12-19 | Approved
RES-2524083 | Paul Lovato | 79 Elect FINAL | 2025-12-19 | Approved
RES-2524083 | Paul Lovato | 59 Plmg FINAL | 2025-12-19 | Approved
RES-2524083 | Paul Lovato | 39 Mech FINAL | 2025-12-19 | Approved
COM-2517636 | Paul Lovato | 29 Bldg FINAL | 2025-12-26 | Approved
RES-2506543 | Paul Lovato | 83 Bldg-Roof In Progress | 2025-12-30 | Approved
RES-2513021 | Paul Lovato | 29 Bldg FINAL | 2025-12-31 | Approved
RES-2513021 | Paul Lovato | 79 Elect FINAL | 2025-12-31 | Approved
RES-2513021 | Paul Lovato | 59 Plmg FINAL | 2025-12-31 | Approved
RES-2513021 | Paul Lovato | 39 Mech FINAL | 2025-12-31 | Approved

## Parcel Conditions
PARCEL | CONDITION NAME | CONDITION COMMENT | APPLIED BY | APPLIED DATE
1202530040000 | Housing | Citizenserve case #25-000038 Interior remodel with new windows. | Paul Lovato | 2025-01-03
11700110370000 | Housing | Citizenserve case #25-000754 Repairs to roof framing | Paul Lovato | 2025-01-09
3601530110000 | Housing | Citizenserve case #23-019583 CMU block wall repair - Remove or permit awning. | Paul Lovato | 2025-01-14
2300720020000 | Housing | Citizenserve case # 25-002315 New roof installed with out permits | Paul Lovato | 2025-01-17
1402510470000 | Housing | Citizenserve case #25-002284 New roof at detached garage. Detached garage turned in to habitable space. | Paul Lovato | 2025-01-23
903610220000 | Housing | Citizenserve case #25-003753 Clear up expired permits RES-0900739 & RES-2104118 & New windows installed. | Paul Lovato | 2025-02-05
2701150240000 | Housing | Citizenserve case #25-005802 Un permitted Interior remodel / New roof | Paul Lovato | 2025-02-24
2701930130000 | Housing | Citizenserve case #25-006044 New roof required. | Paul Lovato | 2025-02-26
2701150140000 | Housing | Citizenserve case #25-006440 New roof required. | Paul Lovato | 2025-02-28
4000210480000 | Housing | Citizenserve case #25-009093 Repair water damage at bathroom. | Paul Lovato | 2025-03-21
2302110060000 | Housing | HSG case #25-013081 New roof required. | Paul Lovato | 2025-04-09
1003240110000 | Housing | Citizenserve Case #25-012987 Replace 5 windows at unit #5 | Paul Lovato | 2025-04-14
27401100450000 | Housing | Citizenserve case #25-014086 Wall removed between adjoining suites 610 & 608 with out permits. | Paul Lovato | 2025-04-16
3802730180000 | Housing | Citizenserve case #25-013939 | Paul Lovato | 2025-04-21
7901820260000 | Housing | Citizenserve Case #25-015735 Double doors added in demising wall between 2 suites. | Paul Lovato | 2025-04-29
2700960080000 | Housing | Citizenserve case #25-018476 Detached accessory structure built with out permits. | Paul Lovato | 2025-05-14
1101270200000 | Housing | Citizenserve case #25-018539 | Paul Lovato | 2025-05-22
1003050110000 | Housing | Citizenserve case #25-019490 New stairs required at front of building. Plans required | Paul Lovato | 2025-05-27
2300620120000 | Housing | Citizenserve case #25-020612 Demolition of existing dwelling unit. Grading of lot for new development. | Paul Lovato | 2025-06-17
2701730190000 | Housing | Citizenserve Case #25-023043 | Paul Lovato | 2025-06-23
1500840150000 | Housing | Citizenserve case #25-023770 Installation of new windows. | Paul Lovato | 2025-06-23
1003650030000 | Housing | Citizenserve case # 25-023473 New stairs at front of property and repairs to decking. | Paul Lovato | 2025-06-24
1401960020000 | Housing | Citizenserve case #25-024584 Fire damage at property. | Paul Lovato | 2025-07-01
2302520080000 | Housing | Citizenserve case #25-025299 | Paul Lovato | 2025-07-03
2103310610000 | Housing | Citizenserve case #25-025669 Additional dwelling unit built in backyard with out permits | Paul Lovato | 2025-07-10
2000720230000 | Housing | Citizenserve case #25-027104 Structure built in backyard | Paul Lovato | 2025-07-29
1500810060000 | Housing | Citizenserve case #25-030565 Interior remodel. | Paul Lovato | 2025-08-12
1402220260000 | Housing | Citizenserve case #25-030013 Bathroom remodel required | Paul Lovato | 2025-08-19
2702950090000 | Housing | Citizenserve case #25-033801 Shed in backyard to be permitted | Paul Lovato | 2025-09-03
1102240020000 | Housing | Citizenserve case #25-030499 | Paul Lovato | 2025-09-10
1202320250000 | Housing | Citizenserve case #25-031248 | Paul Lovato | 2025-09-10
1901130140000 | Housing | Ctitzenserve case #25-035231 | Paul Lovato | 2025-09-18
2701930100000 | Housing | Citizenserve case #25-035445 Un permitted ADU built in back of property built with out permits. Plans required. | Paul Lovato | 2025-09-23
3802720010000 | Housing | Citizenserve case #25-037296 | Paul Lovato | 2025-09-24
7904300190000 | Housing | Citizenserve case #25-038051 Grading vacant lot without permits. | Paul Lovato | 2025-09-30
1102220260000 | Housing | Citizenserve case #25-035532 | Paul Lovato | 2025-09-30
3601140200000 | Housing | Citizenserve case #25-040734 Illegal garage conversion | Paul Lovato | 2025-10-27
1002160070000 | Housing | Citizenserve case #25-041529 | Paul Lovato | 2025-10-29
1101130110000 | Housing | Citizenserve case #25-041319 Remove unpermitted bedroom in attic space | Paul Lovato | 2025-10-30
4902810200002 | Housing | Citizenserve case #25-040820 | Paul Lovato | 2025-11-03
903510050000 | Housing | Citizenserve case #25-040210 Whole house remodel | Paul Lovato | 2025-11-04
2101120220000 | Housing | Citizenserve case #25-044096 Repair or replace roofing materials | Paul Lovato | 2025-11-25
3803460160000 | Housing | Citizenserve case #25-042999 Room built in garage | Paul Lovato | 2025-12-01
1902120190000 | Housing | Citizenserve case #25-046337 | Paul Lovato | 2025-12-12
11800620140000 | Housing | Citizenserve case #25-046277 Unit #80 damaged due to fire. | Paul Lovato | 2025-12-16
3801010090000 | Housing | Citizenserve case #25-042431 Roof repairs and ceiling repairs in unit #1 | Paul Lovato | 2025-12-17